## Task List
Task No | Demand Story | User Story Ref. No. | User Story | Reason | Acceptance Criteria | Software Task | Deliverable | Priority | Story Points (DEV) | Story Points (QA) | Total Story Points | Assigned (Dev) | DEV Start End Date | DEV Target End Date | DEV Status | Assigned (QA) | QA Start End Date | QA Target End Date | QA Status | Remarks
36 | Dynamic Role Based Access - Authorization | US-009 | As a System Administrator, I should be able to configure Role-Based Access (RBA) to assign authority only to authorized users and define specific permissions for each role. *** Please see details "RBA - Checklist" *** | * To ensure that only authorized personnel can perform sensitive actions such as test approvals, report generation, and data validation. * To maintain data integrity, accountability, and compliance with laboratory and organizational standards. * To provide clear role definitions that prevent unauthorized access and reduce risks of errors or misuse. * To enable auditability, ensuring every action is traceable to a specific role and user. | 1. Role Configuration * The system must allow administrators to define and configure specific roles (e.g., Client, Data Entry, Analyst, Supervisor, Approver). 2. Access Control * Given a user logs in, When the system checks their assigned role, Then the user must only see and access features permitted for that role. 3. Restricted Actions * Given a user attempts an action outside their authority (e.g., a client trying to approve a test), When the system validates their role, Then the action must be blocked and logged. 4. e-COA Generation * Only authorized roles (Supervisors/Approvers) must be able to generate and release the official e-COA in PDF format. 5. Internal Reports * Only Data Entry Personnel must be able to generate Excel reports, and these must be labeled “For Internal Use Only.” 6. Audit Trail * All role-based actions (approvals, report generation, data entry) must be recorded with username, role, timestamp, and action. *** Please see details "sample RBA" *** |  |  |  | 16 | 4 | 20 |  |  |  | Not Started |  |  |  | Not Started | Tentative story point. To check first the current framework
37 | Database schema Development | US-010 |  |  |  | Database Schema Setup: Create Samples table with fields (Sample ID, Lab Code, Client Info, Test Type, Date Received, Status, etc.). |  |  | 40 | 0 | 40 |  |  |  | Not Started |  |  |  | Not Started | Dev will revisit as they have to conduct assessment first. PMO allotted 5 Mandays for the database development.
38 | [5 empty] | Extend database schema to capture verification details (e.g., labeling, container, integrity check, verifier name, verification date).
39 | [5 empty] | Extend schema for assignment of samples to analysts (e.g., including turnaround time, test type).
1 | Sample Registration | US-001 | As a Receiving Staff/QA Lab Analyst, I want to log incoming samples, assign a unique Job Code, and record client/test details so each sample can be accurately tracked from intake to reporting. | Ensure traceability and accountability for all samples from receipt to reporting. | ▪️All samples logged in the system must have a unique Laboratory Code assigned at registration. ▪️Client details, sample descriptions, requested tests, and timestamps must be accurately captured. ▪️Verification steps must identify and flag any labeling or container discrepancies before testing. ▪️Preparation records must include personnel name, date/time, and notes for traceability. ▪️Test results must pass validation rules before supervisor review. ▪️Reports/COAs must be approved before release to clients. ▪️Clients must be able to access final reports securely via portal, email, or physical copy. ▪️The system must update sample status appropriately at each process step (e.g., ""Sample Registration,"" ""Verified,"" ""Preparing,"" ""In Analysis,"" ""Data Entry,"" ""Verifying Results,"" ""Reported"")." | Lab Code Generator: Implement unique Laboratory Code generator (e.g., LAB-YYYYMMDD-XXX). | A functional Sample Intake Module where Receiving Staff can log samples, automatically generate Lab Codes, and record all client/test details, with traceability for downstream processes. |  | 24 | 8 | 32 |  |  |  | Not Started |  |  |  | Not Started
2 | [5 empty] | Sample Intake Module (UI): Build frontend form for Receiving Staff to enter client/test details and auto-generate Lab Code.
3 | [5 empty] | Validation Rules: Enforce mandatory fields (e.g., Client Name, Sample Type, Requested Test) and error handling for duplicates
4 | [5 empty] | Workflow Status Tracking: Add status progression (e.g "Received → Pending Verification.")
5 | [5 empty] | Unit Test: Verify that the system generates a unique Laboratory Code for every new sample logged.
6 | Verification | US-002 | As a Verification Team/QA Lab Analyst, I want to check sample labeling, containers, and integrity against the client submission form so only valid and compliant samples proceed to testing. | Maintain accuracy and compliance with laboratory quality standards. |  | Create Verification Module (UI form) to review sample details vs. client submission form. | Verified samples with recorded compliance details, ready for lab preparation. |  | 16 | 8 | 24 |  |  |  | Not Started |  |  |  | Not Started
7 | [5 empty] | Implement status update logic: (e.g., "Pending Verification → Verified/Rejected.")
8 | [5 empty] | Build validation rules to ensure required checks are performed before approval.
9 | [5 empty] | Unit Test: Conduct unit testing for the verification workflow.
10 | Preparation 1 | US-003 | As a Lab Preparation Staff/Lab Aide, I want to perform pre-analytical processes (e.g., grinding, homogenizing) and record preparation details so samples are ready for accurate testing. | Maintain sample integrity and readiness for analysis. |  | Add Pre-Analytical Data Fields e.g., (method, preparation notes, staff name, timestamp). | Prepared samples with complete pre-analytical records. |  | 8 | 2 | 10 |  |  |  | Not Started |  |  |  | Not Started
11 | [5 empty] | Create Preparation Module (UI form) linked to verified samples.
12 | Preparation 2 | US-004 | As a QA Lab Analyst, I want to perform pre-analytical processes (e.g., grinding, homogenizing) and record preparation details so samples are ready for accurate testing. | Maintain sample integrity and readiness for analysis. |  |  | Prepared samples with complete pre-analytical records. |  | 16 | 2 | 18 |  |  |  | Not Started |  |  |  | Not Started | Large on the assumption that there is a notification requirement for Preparation 2. Else, Medium
13
14
15 | Test Execution and Data Entry | US-005 | As QA Lab Analyst, I want to receive prepared samples with logged parameters and expected turnaround times so I can begin testing according to requirements. | Ensure efficient test assignment and adherence to deadlines. |  | Build Sample Assignment Module (e.g., UI: view list of prepared samples, assign analyst, due dates). | Analysts can receive samples with full parameters and assigned timelines. |  | 16 | 4 | 20 |  |  |  | Not Started |  |  |  | Not Started
16 | [5 empty] | Add notification/queue system to alert analysts of assigned samples.
17 | [5 empty] | Implement status tracking: (e.g., Prepared → In Testing.)
18 | [5 empty] | Unit Test: Test workflow for correct assignment and tracking.
20 | Data Review | US-006 | As a Data Entry Personnel/QA Lab Analyst, I want to enter test results into the Analysis Worksheet with validation rules so the data is accurate and free from common input errors. | Reduce manual errors through automated validation. |  | Create Analysis Worksheet Module (UI form) linked to each sample/test. | Accurate, validated raw results recorded in the system. |  | 16 | 4 | 20 |  |  |  | Not Started |  |  |  | Not Started | Notification is required 16, else 8
21 | [5 empty] | Implement validation rules (e.g., numeric ranges, mandatory fields, format checks).
22 | [5 empty] | Add auto-save and version history for result entries.
23 | [5 empty] | Build backend logic to mark results as "Pending Review."
24 | [5 empty] | Unit Test: Conduct unit testing for the data entry validation.
25 | Result Verification | US-007 | As an Authorized Lab Personnel, I want to review and validate test results so only verified data is used in final reports. | Ensure accuracy and reliability of reported results. |  | Add Review & Validation Module where authorized staff can review entered results. | Verified and approved test results ready for reporting. |  | 16 | 4 | 20 |  |  |  | Not Started |  |  |  | Not Started | Notification is required 16, else 8
26 | [5 empty] | Implement approval/rejection workflow with digital sign-off.
27 | [5 empty] | Create audit trail of who validated results and when.
28 | [5 empty] | Ensure role-based access (only authorized personnel can validate).
29 | [5 empty] | Unit Test: Test approval workflow end-to-end.
30 | Report Release | US-008 | As a Client/Requester, I want to receive the Official Test Report or Certificate of Analysis in a secure and accessible format so I can review my results promptly and reliably. | Provide clients with secure, timely, and accessible reports. |  | Develop Report Generation Module (PDF/Excel formats for COA). | Secure, client-accessible Certificate of Analysis (COA). |  | 40 | 4 | 44 |  |  |  | Not Started |  |  |  | Not Started | To revisit the story points during the development.
31 | [5 empty] | Implement secure access control (e.g., login, tokenized links, encryption).
32 | [5 empty] | Build report distribution (e.g., email, portal download).
33 | [5 empty] | Add report templates with client details, test results, validation signatures.
34 | [5 empty] | Ensure that the test results are accessible to authorized personnel only. (Nutritionist)
35 | [5 empty] | Unit Test: Test secure report access across devices.
40 | Transfer of Laboratory Process | US-011 | [6 empty] | 40 | 40 | 80 |  |  |  | Not Started |  |  |  | Not Started | To be revisited by the dev and QA team
41 | Planning and test case creation of QA | US-012 | [6 empty] | 0 | 16 | 16 |  |  |  | Not Started |  |  |  | Not Started | As per confirmation from QA Dex 9/23/2025
[8 empty] | Total Story Points | 192 | 92 | 284
[8 empty] | Estimated Mandays | 24 | 11.5 | 35.5